QUOTATION

| Attn | Click or tap here to enter text. | Date | Click or tap here to enter text. |
| --- | --- | --- | --- |
| Company | Click or tap here to enter text. | Ref No. |  |
| Address | Click or tap here to enter text. | Tel No. | Click or tap here to enter text. |
|  | Click or tap here to enter text. | Email | Click or tap here to enter text. |
|  | Click or tap here to enter text. | Validity | 30 days |

SUBJECT: TO SUPPLY MATERIALS FOR Click or tap here to enter text. KWP GRID CONNECTED SOLAR PV SYSTEM

1.0 SCOPE OF WORK

| No | Item | Qty |
| --- | --- | --- |
| 1 | Supply Solar PV Module with a cumulative capacity of Click or tap here to enter text.kWp - Trina Solar Mono-crystalline half-cell with MyHijau mark or equivalent. - 15 years on product material and workmanship warranty from manufacturer. - 30 years linear output warranty from manufacturer. | Click or tap here to enter text. units (620Wp) |
| 2 | Supply Solar Inverter with a cumulative capacity of Click or tap here to enter text.kWac - Click or tap here to enter text. high efficiency string inverter with MyHijau mark or equivalent. - 10 years product warranty. | 1 set |
| 3 | Supply roof mounting structure - Tile/Tin roof mounting structure, complete with rail, clamp and connector. - 10 years product warranty. | 1 set |
| 4 | Supply Balance of System/Accessories - Combiner box, breaker, accessories and all necessary wiring for power and communication. - 2 years product warranty. | 1 set |
|  | TOTAL PRICE: RM Click or tap here to enter text. |  |

2.0 NOTES

2.4 Product warranty will be void if the parts defects due to third party fault/ vandalism/ act of God/ Grid Error.

3.0 PAYMENT TERM

3.1 Our progressive payment term as below: -

i. 10% upon acceptance and signing of quotation.

ii. 50% upon SEDA approval.

iii. 35% upon complete installation, before submission to TNB

iv. 5% upon complete TNB Commencement of Operation Date (COD).

4.0 PROJECT DURATION

4.1 The project workflow as below: -

i. Connection Assessment Study with TNB Approval: 4-6 weeks (for system size above 100kWp)

ii Technical assessment and SEDA ATAP application: 4-6 weeks

iii. Stock preparation: Ex-stock or 4-6 weeks order

iv. Installation and configuration: 4-6 weeks, subject to weather constraints (300 – 600 kWp)

v. ST License application and approval: 3 months (for system size above 100kWp)

vi. Change of TNB bi-directional meter: 2-4 weeks, subject to TNB arrangement

vii. Handover and system update: 1 week

Prepared by:							Accepted by:

ASTERN TECHNOLOGIES SDN. BHD.

Name: LENG RONG CHEN					Name:

Position: DIRECTOR						Position:

Date:								Date:

QUOTATION

| Attn | Click or tap here to enter text. | Date | Click or tap here to enter text. |
| --- | --- | --- | --- |
| Company | Click or tap here to enter text. | Ref No. |  |
| Address | Click or tap here to enter text. | Tel No. | Click or tap here to enter text. |
|  | Click or tap here to enter text. | Email | Click or tap here to enter text. |
|  | Click or tap here to enter text. | Validity | 30 days |

SUBJECT: TO CONSTRUCT AND INSTALL Click or tap here to enter text. KWP GRID CONNECTED SOLAR PV SYSTEM

1.0 SCOPE OF WORK

| No | Item | Qty |
| --- | --- | --- |
| 1 | Construction and Installation of Solar PV Module and Solar Inverter - Click or tap here to enter text. kWp Trina Solar PV Module - Click or tap here to enter text. kWac Solis/Huawei Inverter | 1 set |
| 2 | Install roof mounting structure - Tile/Tin roof mounting structure, complete with rail, clamp and connector. | 1 set |
| 3 | Install Balance of System/Accessories - Combiner box, breaker, accessories and all necessary wiring for power and communication. | 1 set |
| 4 | Testing & Commissioning (T&C) - System installation is in accordance to MS1837 of the Malaysian Standard Installation of Grid Connected Solar System. | 1 set |
| 5 | Supply Technical Drawings and Authority Submission - Drawings, Technical Design, and ATAP related application to SEDA and TNB. | 1 set |
| 6 | Operation & Maintenance - Annual cleaning, technical support, online monitoring, preventive check, visual and thermal inspection of hot spots, and data log analysis. | 1 year |
| 7 | Defect Liability Period - Labor warranty and roof water-leakage warranty from the date of successful commissioning. | 1 set |
|  | PRICE: RM Click or tap here to enter text. |  |
|  | SST 6%: RM Click or tap here to enter text. |  |
|  | GRAND TOTAL : RM Click or tap here to enter text. |  |

2.0 NOTES

2.1 Quotation does not include any modification to existing electrical network if required by TNB. PV System will be connected directly to the main incoming of the facility’s existing MSB.

2.2 Reinforcement of roof to cater for the additional load of the PV panels will be quoted separately if required.

2.3 Final system size will depend on detail site survey and roof space measurement upon confirmation of order.

2.4 Down payment is non-refundable, except when SEDA is not approved or roof installation is not possible after site visit.

3.0 PAYMENT TERM

3.1 Our progressive payment term as below: -

i. 10% upon acceptance and signing of quotation.

ii. 90% upon SEDA approval.

Remark: To ensure smooth project handover and system performance, we kindly request full payment upon installation completion. In cases of delayed payment, system operation may be temporarily paused, and further action may be considered if unresolved. We appreciate your support and understanding.

4.0 PROJECT DURATION

4.1 The project workflow as below: -

i. Connection Assessment Study with TNB Approval: 4-6 weeks (for system size above 100kWp)

ii Technical assessment and SEDA ATAP application: 4-6 weeks

iii. Stock preparation: Ex-stock or 4-6 weeks order

iv. Installation and configuration: 4-6 weeks, subject to weather constraints (300 – 600 kWp)

v. ST License application and approval: 3 months (for system size above 100kWp)

vi. Change of TNB bi-directional meter: 2-4 weeks, subject to TNB arrangement

vii. Handover and system update: 1 week

Prepared by:							Accepted by:

ASTERN TECHNOLOGIES SDN. BHD.

Name: LENG RONG CHEN					Name:

Position: DIRECTOR						Position:

Date:								Date: